## Sheet1
RESEARCH PROJECT TIMELINE
Quantum Optimisation for the Vehicle Routing Problem
Drestanto Muhammad Dyasputro - 1450107
semester
| 1 (2025 first half) | [11 empty] | 2 (2025 second half)
activity \ week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | fin
Topic Formulation
Create research topic brief write up
Make the case stronger, define data sources, construct timeline
finalize topic
Literature Review
Explore quantum algorithms and circuits (QAOA, Quantum Walk, VQE, Quantum Annealing)
Review existing research on quantum optimization for VRP
Research Methodology Formulation
Develop research methodology to approach VRP using quantum optimization
create structured proposal draft
Research Proposal Drafting
Write research proposal with objectives, methodology, and case study specifics
submit research proposal
Data Acquisition
Collect data from real-world sources
create data flow plan
Oral Presentation
prepare oral presentation
present to supervisor
oral presentation: research progress
Quantum Algorithm Formulation
Data Translation
Translate spatial data into a VRP-compatible graph
Quantum Algorithm Formulation and Implementation
Benchmarking Strategy
Algorithm Optimization
Thesis paper preparation and finalization
paper preparation
enhancement
finalization and submission